Faster access to specialist mental health and addiction services

2030 target = 80%

This measure shows the percentage of people accessing specialist MH&A services seen within three weeks of referral.

National result

Results by region

Northern Te Manawa Taki Central | Ikaroa Te Waipounamu

Target

85.6

78.5

Results by district

Taranaki West Coast South Canterbury

MidCentral Auckland Hawkes Bay

Counties Manukau

Waitematā Waikato Northland Bay of Plenty Southern Whanganui

Lakes Canterbury Hutt Valley

Nelson Marlborough Capital and Coast

Wairarapa Tairāwhiti

Target

84.7

83.4

82.0

79.6

78.8

78.3

77.6

77.1

77.1

73.4

71.8

69.4

69.0

80.6

82.0

Shorter mental health and addiction-related stays in EDs

2030 target = 95%

This measure shows the percentage of mental health related ED attendances that were admitted, discharged or transferred from an ED within six hours as a proportion of all mental health related attendances.

National result

Results by region

Te Waipounamu Te Manawa Taki Central | Ikaroa

Northern

Milestone

Target

85.2

76.9

Results by district

West Coast South Canterbury

Southern Tairāwhiti Canterbury

Nelson Marlborough

Northland

Lakes Waikato

Bay of Plenty Hawke's Bay Taranaki Whanganui MidCentral Auckland Wairarapa Hutt Valley Waitematā

Counties Manukau Capital and Coast

55.2

52.5

Milestone

Target

94.4

91.7

86.4

85.7

85.0

81.9

81.4

79.8

76.2

75.7

74.3

74.1

70.2

62.7

60.5

60.5

52.1

44.6

40.4

36.2

| 91.3 |  |
| --- | --- |
| 90.4 |  |
| 89.9 |  |
| 88.2 |  |
| 87.8 |  |
| 86.5 |  |
| 85.7 |  |

Faster access to primary mental health and addiction services

2030 target = 80%

This measure shows the percentage of people accessing primary MH&A services through the Access and Choice programme within one week.

National result

Results by region

Northern Te Waipounamu Te Manawa Taki Central | Ikaroa

Target

85.1

84.9

84.4

81.4

Results by district

Waikato Southern West Coast Auckland Whanganui MidCentral Northland Bay of Plenty

Counties Manukau

Lakes Hawke's Bay Canterbury Waitematā Capital and Coast South Canterbury

Wairarapa Nelson Marlborough

Hutt Valley Taranaki

Target

98.2

91.6

91.2

88.4

88.1

86.8

86.7

84.6

84.4

84.4

83.7

82.5

82.0

80.5

80.0

77.6

77.6

71.8

70.0

Tairāwhiti UNAVAILABLE (see caveats)

All figures displayed are percentages.

Increased mental health and addiction workforce development

Target = 500 more trained yearly

National result

Semester 1

2025 result

This measure shows the number of mental health and addiction professionals trained each year in New Zealand.

Q3 overview

349 people in the identified professions started their training in semester one of the 2025 calendar year. This is a partial result as some professions also have a second semester intake. The full result for this measure will be reported in Q2 2025/26.

Some of the national initiatives to support improvements include:

Training of peer support workers, with contracts in place for the delivery of Level 4 Health and Wellbeing (Peer Support) Training to further support this workforce.

The number of people entering New Entry into Specialised Practice training remains strong with 200 enrolled and starting nursing, and 51 in allied training so far in 2025.

Shorter mental health and addiction- related stays in EDs

Q3 overview

Performance has improved and 12 out of 20 districts have met the milestone.

The strong performance in Te Waipounamu can be attributed to the physical proximity of crisis teams to emergency departments and strong points of contact between teams that enables consistent early planning.

Steps to improve performance in districts in the Northern and Central regions include:

Counties Manukau and Waitematā have established a consistent approach to support engagement across their teams, utilising escalation plans and/or alternative admission pathways.

Auckland is working with partner agencies to address occupancy pressures in Te Whetu Tawera (inpatient unit), where barriers to discharge have housing, social, and dual diagnosis drivers.

Northland is trialling a simultaneous physical and mental health and addiction assessment approach and will share their learnings with other districts.

In March, the Wellington City Mission Crisis Café and the peers in the emergency department initiatives began at Capital and Coast.

Collaboratively, Capital and Coast, Hutt Valley, and Wairarapa are working with NGO sector to explore opportunities to partner and expand the number of acute step-down / alternative placement options.

Faster access to primary mental health and addiction services Q3 overview

All regions have achieved the 80 per cent target, with Northern being the best performing region.

Activity continued in Central region this quarter to improve performance:

Review meetings with Integrated Primary Mental Health and Addictions Services (IPMHA) providers commenced with a focus on improving accurate data collection and reporting against the targets. MidCentral, Whanganui and Hawke’s Bay review meetings were completed in quarter three, and Wellington, Wairarapa and Capital and Coast are scheduled for early in quarter four.

MidCentral introduced a new data collection tool to improve reporting accuracy.

Faster access to specialist mental health and addiction services

Q3 overview

All regions are focused on sustaining or improving performance.

One of the best performing districts, West Coast has a new model of care that supports more timely triaging of adult referrals.

Te Waipounamu, the only region not to achieve the target, is building a picture of the barriers to success to inform planning.

Canterbury is undertaking a model of care review to improve access to treatment and streamline the flow through services.

Nelson Marlborough has recruited a nurse practitioner to initiate a Clozapine clinic, to transfer care management of patients to a single point in the service and improve capacity for intake of patients.

Waikato is implementing lessons from its quality improvement reviews on waitlists, referrals and capacity. Actions include care co- ordination management; implementing a prioritisation matrix; conducting caseload flow meetings and adopting data-driven operational management approaches. The region will share these findings with other districts.

Strengthened focus on prevention and early intervention

2030 target = 25%

National result

This measure presents the proportion of mental health and addiction ringfenced investment allocated to prevention and early intervention.

Q3 overview

This result is the annual budgeted investment; it does not represent the proportion of the mental health and addiction ringfence that has been spent during the quarter.

Activity this quarter includes the completion of a request for proposal for a mental wellbeing promotion campaign, with contract negotiations underway. Additionally, increased investment in maternal mental health services and infant, child and youth services in districts with the lowest levels of investment continues.