## Slide 1
Health Workforce Plan
Progress Report
Dec 24 – 30 June 25

## Slide 2
Summary
Health Workforce Implementation Plan – Progress Overview (Dec 2024 – June 2025)
This report provides a comprehensive update on the initiatives that commenced delivery in late December 2024 under the Health Workforce Implementation Plan (HWP). It reflects the first full reporting period and sets the foundation for quarterly updates going forward.
The initiatives included in this report are those that actively began delivery in 2024.
Any initiatives not included in this report are scheduled for delivery in future years (2025/2026 and 2026/2027) and will be reported on as they progress into implementation.
Progress Snapshot
Total Initiatives Reported: 36
On Track for Delivery (Green RAG): 27 initiatives
Some Risk but Being Managed (Yellow RAG): 8 initiatives
Completed: 1
The report highlights achievements across all five priority areas, including:
Establishment of national clinical student placement access agreement
Expansion of training programmes in primary care, mental health, and rural settings
Development of new assistant roles and advanced practice pathways
Continued investment in Māori and Pacific workforce development

## Slide 3
Priority 1
Get our workforce basics right
The new national clinical student placement access agreement replaces over 400 varying contracts between the former DHBs and education providers
107 healthcare and education leaders explored the Dedicated Education Unit (DEU) model to optimise workforce development and student placement
Digital coordination tool successfully piloted with Anaesthetic Technicians 221 Placements confirmed for semester one 2025
Radiation Therapy Programme: University of Otago confirmed 43 first year enrolments for 2025, up from 23 in 2024
Tertiary Training Programme Growth: AUT reported a 28% increase in student enrolments for
the Perioperative
Practitioner programme
Priority 2
Work differently for productivity and better care
Protective security programme implemented to keep frontline Health NZ staff safe reinforcing our commitment to protecting people, assets, and information
Managing Health Challenges at Work Policy implemented to establish a consistent and equitable approach to supporting employees managing health challenges across HNZ
Work-Related Injury and Rehabilitation Policy implemented committing to early intervention, effective rehabilitation, and ensuring a safe return to work for our employees. Health NZ is now an accredited employer under the ACC programme
Five new Long-Term Micro credentials approved in collaboration with NGOs and Toitū te Waiora. For more info Update on long-term health conditions skill standards, qualification, and micro-credential development - Toitū te Waiora
To fund learner’s enrolment fees to the Level 4 NZ Certificate in Health and Wellbeing (Peer Support)
Priority 3
Keep people well, close to home through primary care
121 Nurse Practitioners in training 2025 194 GPEP year ones in training, 2025 Supporting an additional 22 people on Rural Medical Immersion Programme to supplement the numbers supported by the Universities of Otago and Auckland
A pilot programme for funding Primary and Community employers available for up to 200 graduate Registered Nurses, to gain employment in a primary and community setting
Launch of fund to support 400 Graduate Registered Nurses into Primary and Community setting
Establish Psychology Assistant training programme:
Working with the NZ Psychologists Board to establish the regulatory requirements for Psychology Assistants
Procurement completed with University of Canterbury for development of postgraduate diploma programme for training the Psychology Assistant workforce.
Priority 4
Address workforce needs to hit targets
13 new Basic Public Health Registers in training
226 Midwives supported through the Midwifery First Year of Practice
Growth in current medical school student numbers 50 additional students started in 2024, followed by 25 more in 2025 and 25 in 2026.
Detailed Business Case (DBC) for potential New Medical School
462 International hires from over 8000 expressions of interest across Health New Zealand.
Priority 5
A workforce that reflects community need
925 newly qualified health professionals are set to receive financial support through the Voluntary Bonding Scheme
476 Registered and Enrolled Nurses
172 Midwives
77 Anaesthetic Technicians
70 General Practice Trainees
48 Pharmacists
23 Dentists
22 Oral Health Therapists
20 Radiation therapists
15 Sonographers
1 Medical Physicist
420 Internships with Hauora Māori Partners supported in 2024
1218 scholarships supporting Māori in health studies for 2024
Key Pacific workforce development programmes have been supported to continue
175 Scholarships were awarded for Pacific applicants working in Mental Health and Addictions settings.
21 Pacific kaiāwhina in Northern Region based providers completed a 10 week a Level 3 diabetes micro credential education programme
100% achievement - 33 Pacific trained nurses completed the L7 Diploma in Nursing (Pacific) and passed the Nursing State Exam to become RNs
373 Pacific Health Scholarships awarded for Pacific students studying in health and disability education programmes
The NZ qualification Authority has approved Foot Care Assistant Level 4 qualification and available on the Qualifications Framework. Pilot implementation is in development

## Slide 4
Priority 1
Getting our workforce basics right
Initiative Number | Description | RAG | Current Activity | Next Steps
1.1 | Secure Educational Training Capacity. This initiative focuses on strengthening the pipeline for clinical education and training across key health disciplines, ensuring future workforce sustainability. |  | Podiatry: AUT’s new Graduate Entry Master's (GEM) programme, endorsed by Health NZ, will include prescribing scope training. AUT is also increasing student-led clinic capacity in the Northern Region, with 17 more undergraduate enrolments confirmed for 2025. Oral Health Therapy: AUT students will treat up to 1,400 paediatric patients through a new Auckland Regional Dental Service contract, delivered at South Auckland schools via the Manukau campus clinic. | Continue supporting increased enrolments in Oral Health Therapy and Podiatry for Semester 2, 2025 and Semester 1, 2026. Collaborate with the Planning, Funding & Outcomes (PFO) team to develop student-led clinics, enhancing clinical placement opportunities and exposure.
Key Achievements |  |  |  | 
Secured Auckland Regional Dental Service contract enabling up to 1,400 oral health patient referrals for student training. Achieved a 17-student increase in Podiatry undergraduate enrolments for 2025. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
1.2 | Boost Health NZ’s Placement Capacity. This initiative is focused on expanding and standardizing clinical placement capacity across Health NZ. |  | The national clinical student placement access agreement is being implemented. Relationship Managers oversee access and scheduling through local and national meetings Preparing to include pre-registration medical students in the national agreement. | Engagement with Health NZ Chief Medical Officers and medical schools. Ongoing support for implementation and issue resolution.
Key Achievements |  |  |  | 
A single National Clinical Student Placement and Access Agreement has been signed by all tertiary education providers, replacing over 400 previous contracts. Relationship Manager meetings have been held to support implementation and oversight. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 5
Priority 1
Getting our workforce basics right
Initiative Number | Description | RAG | Current Activity | Next Steps
1.2.2 | Boost Health NZ’s Placement Capacity (Medical) Expanding medical placement opportunities, with a focus on rural hospitals, other hospital settings, and primary care |  | Ongoing work with RDSS to map priority PGY1 and PGY2 placement sites across rural and primary care settings as part of primary care pathway for domestic graduates which is included in the funded primary care tactical action plan (PCTAP). | Next steps include appointing an integration lead to support Public Health Medicine Registrars and facilitate the rollout of expanded medical placement opportunities.
Key Achievements |  |  |  | 
Completed Expression of Interest process to identify practices and districts for additional PGY1 placements for domestic graduates. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
1.2.1 | Boost Health NZ’s Placement Capacity (Allied and Specialist Nursing) Expanding clinical placements for allied and specialist nursing, with a focus on diverse settings. |  | Regional DEU network rollout 24/7 nursing placement pilot expansion | Completed action
Key Achievements |  |  |  | 
Regional Dedicated Education Unit (DEU) networks established and supported nationally National guidelines and resources published for all districts Over 250 placement schedules analysed across professions First national DEU symposium held (Nov 2024) |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 6
Priority 1
Getting our workforce basics right
Initiative Number | Description | RAG | Current Activity | Next Steps
1.5 | Improve Use of Simulation This initiative aims to enhance the use of simulation in health education by building a national network and improving access to shared resources. |  | The national simulation group is defining requirements for a nationwide stocktake of simulation resources. | Conduct a national stocktake of simulation resources.
Key Achievements |  |  |  | 
Simulation network established. Online hub of simulation resources created. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
1.4 | Streamline Tertiary Training Programmes (Nursing) Improving access to nursing education by aligning entry pathways for Enrolled Nurses (EN) into Bachelor of Nursing programmes |  | Recognition of Prior Learning (RPL) criteria for Enrolled Nurse entry are being standardised. Transition papers in science and pharmacology are being aligned across tertiary providers. | Awaiting updates from tertiary education organisations on progress
Key Achievements |  |  |  | 
National mapping of the current Enrolled Nurse workforce completed. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 7
Priority 1
Getting our workforce basics right
Initiative Number | Description | RAG | Current Activity | Next Steps
1.9 | Improve National Workforce Planning This initiative aims to strengthen national health workforce planning by developing data-driven models that reflect real-world service needs and workforce trends. |  | A prototype bottom-up planning tool has been piloted in radiology and urgent care. The nursing workforce model has been updated to incorporate education and immigration trends Initial improvements made to nursing workforce model, incorporating education and immigration trends. Union workforce planning data group launched. New planning models shared for sector feedback | Commence scoping work on national psychiatry stocktake
Key Achievements |  |  |  | 
Bottom-up workforce planning tool created and tested. Nursing model updated to reflect future workforce supply. Sector engagement initiated through union data group and model socialisation. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
1.6 | Improve Student Placements This initiative aims to streamline and strengthen student clinical placements across the health sector through a co-designed digital tool and coordinated support systems. |  | Anaesthetic technicians are actively using the digital tool to plan Semester 2, 2025 placements. Placement Hub support is in place and operational. | Develop business case for continued tool development and rollout. Commission independent evaluation of the programme.
Key Achievements |  |  |  | 
Strategic Steering Group established with agreed Terms of Reference. Co-design completed; first version of the digital tool launched. Anaesthetic technicians onboarded and placements planned for semester one 2025. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 8
Priority 2
Work differently for productivity and better care
Initiative Number | Description | RAG | Current Activity | Next Steps
2.3 | Improve Support for Progression This initiative focuses on identifying and improving career progression pathways for Kaiāwhina roles, particularly those with unclear development opportunities. |  | A draft list of Kaiāwhina roles with unclear progression pathways (e.g., orderlies) has been developed for review. Kaiāwhina refers to workforce roles that typically involve direct caregiving, support, or health-related services which are sometimes referred to as the care and support workforce. | Establish a Health NZ stakeholder group to confirm and prioritise roles for workforce development.
Key Achievements |  |  |  | 
Initial scoping of non-mental health Kaiāwhina roles completed. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
2.5 | Launch Flagship Services to Keep Staff Well at Work. This initiative is focused on launching key services that support staff wellbeing and help keep people well at work. |  | The Occupational Health Service is undergoing comprehensive consultation with staff and unions. Several service components are nearing final decisions, while key areas require continued engagement with union partners. Despite timing pressures, the programme remains on track to confirm and establish a nationally consistent and equitable occupational health service for staff within the 2025/26 financial year. | Finalise clinical position descriptions in partnership with unions.
Key Achievements |  |  |  | 
Extensive engagement with staff and unions completed to inform service design. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 9
Priority 2
Work differently for productivity and better care
Initiative Number | Description | RAG | Current Activity | Next Steps
2.8 | Make an Improved National Culture Real This initiative focuses on fostering a respectful, inclusive, and supportive workplace culture across Health NZ. |  | Phase one of Respect at Work launched with positive feedback Leadership Development Programme design and implementation planning underway Organisational wellbeing initiatives available | Continue planning Health NZ’s culture approach Align Respect at Work Phase two with new people policies Expand wellbeing initiatives Launch of Health Leadership Development Programme first cohorts
Key Achievements |  |  |  | 
3,878 Respect at Work sessions or e-learning modules completed Leadership Development Programme in clinical co-design phase |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
2.6 | Keep Our People Safe at Work This initiative focuses on enhancing safety for staff in emergency departments through tailored security training. |  | Finalising the 2024/25 programme completion report Customising training for regional ED security teams | Rollout of the security training programme to: Northland, Tauranga, Whakatāne, Taupō, and Rotorua (Scheduled for August–September 2025)
Key Achievements |  |  |  | 
All deliverables completed on time and within budget Consistently positive feedback from participants and senior staff |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 10
Priority 3
Keep people well, close to home through primary care
Initiative Number | Description | RAG | Current Activity | Next Steps
3.1.2 | Expand Our Foundational Workforces This initiative supports health workers in entry-level roles through targeted education programmes to obtain health qualifications including additional funded training for the consumer, peer support and lived experience (CPSLE) workforce. |  | Cohort 2 of Pacific kaiāwhina in Northern Region Pacific Providers has commenced the Level 3 diabetes micro-credential education programme. | Prepare Cohort 3 in the Central Region to begin the 10-week programme.
Key Achievements |  |  |  | 
Ongoing delivery of diabetes microcredential education to Pacific Kaiāwhina. Contracts in place with two training providers to fund enrolment fees for 90 level 4 NZ Certificate in Health and Wellbeing (Peer Support) places for 2025/26. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
3.1.3 | Expand Our Foundational Workforces (Primary and Community Care) This initiative supports postgraduate education for paramedics, pharmacists, and physician assistants working in primary and community care settings. |  | Finalising contracts with education providers to enable postgraduate study for targeted workforce groups. | Begin collecting enrolment data to monitor uptake and impact.
Key Achievements |  |  |  | 
Contracts in place to support advanced training for primary and community care professionals. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 11
Priority 3
Keep people well, close to home through primary care
Initiative Number | Description | RAG | Current Activity | Next Steps
3.2.2 | Establish and grow assistant roles This initiative focuses on the establishment of a training programme for at least 20 Psychology Assistants per year. |  | University of Canterbury and Auckland University of Technology are beginning consultation on their programmes. They are scheduled to begin delivery of training programme in 2026. The NZ Psychologists Board (NZPB) are working through requirements for the approval of the scope and competencies for the Psychology Assistant role. | Working with NZPB on the delivery of the final and approved scope of practice and competencies. The project’s next phase will focus on developing the employment aspects of the role.
Key Achievements |  |  |  | 
Completed an open procurement resulting in contracts with University of Canterbury and Auckland University of Technology to develop the postgraduate diploma programme to train psychology assistants. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l
Initiative Number | Description | RAG | Current Activity | Next Steps
3.4.2 | Improve Graduate Transitions – Nursing (PCTAP RN 400) This initiative enhances support for nursing graduates transitioning into the workforce through the Primary Care Tactical Action Plan Registered Nurse 400 programme. |  | Since 1 May 2025, 29 employer assessments received, and 22 funding approvals granted Ongoing engagement and advertising to raise awareness of funding opportunities | Weekly employer eligibility reviews and funding application processing Communications plan completed Webinar scheduled for 18 July 2025 for third-year nursing students and graduate RNs
Key Achievements |  |  |  | 
Successful transition from Advanced Choice of Employment (ACE) Registered Nurse (RN) 200 to PCTAP RN 400, with support from Aged Residential Care, Primary and Community Health Care, and Plunket for upcoming webinar. |  |  |  | 

## Slide 12
Priority 3
Keep people well, close to home through primary care
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l
Initiative Number | Description | RAG | Current Activity | Next Steps
3.5 | Grow Our GP and Community Medical Workforce (domestic primary care pathway) This initiative aims to strengthen the domestic pipeline into general practice and community medical roles through a structured primary care pathway. |  | Develop a transitional process to determine who will participate in the primary care pathway for 2026 EOI for primary care practices to signal interest in pathway Engagement with Districts to establish available flexibility to release PGY2 onto primary care pathway Develop a comms approach for engagement with PGY1s | EOI to identify house officers who want to participate on the pathway Contract with Districts to implement pathway Develop a transitional process to determine who will participate in the primary care pathway for 2027
Key Achievements |  |  |  | 
Sector-wide workshop held in May 2025 to support pathway design Workshop planning for 2026 primary care pathway complete |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
3.5.2 | Grow Our GP and Community Medical Workforce (GPEP) This initiative supports the expansion of the General Practice Education Programme (GPEP) to strengthen the GP and community medical workforce. |  | A briefing paper has been submitted to the Minister outlining funding options for GPEP, including expansion for GPEP2 and GPEP3. | Begin work in July 2025 following Ministerial decision on the briefing.
Key Achievements |  |  |  | 
GPEP funding proposal submitted to the Minister’s Office in June 2025. |  |  |  | 

## Slide 13
Priority 3
Keep people well, close to home through primary care
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l
Initiative Number | Description | RAG | Current Activity | Next Steps
3.6.1 | Bolster Maternity Care (Kai Amo Pōkai) This initiative aims to strengthen maternity care through the development of the Kai Amo Pōkai role. |  | A working group, including Chief Clinical Midwives, has drafted the role description. The final document is now awaiting approval. | Approve the role description and begin implementation milestones in 2025/26.
Key Achievements |  |  |  | 
Draft role description completed through collaborative development. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
3.7 | Extend Scopes Through Training This initiative supports the expansion of clinical scopes through targeted training, with a focus on Nurse Practitioners (NPs) in primary health care. |  | RFP for NP Training Support Fund completed Successful provider to be announced in October 2025 Career and education pathway for new graduate RNs to NP in development Mapping NPs across priority settings based on 2025 trainees | Evaluate proposals and award contract Refine NP distribution map
Key Achievements |  |  |  | 
RFP process successfully completed |  |  |  | 

## Slide 14
Priority 4
Address Workforce Needs to Hit Targets
Initiative Number | Description | RAG | Current Activity | Next Steps
4.3 | Grow Mental Health and Addiction Capacity (Growing psychology intern roles) |  | Conversations have begun with both the tertiary providers and potential employers regarding placement for clinical psychology interns for the 2026 calendar year and proportional allocations of internships notified. | Continuation of conversations to finalise placements for 2026 to allow contracting to begin.
Key Achievements |  |  |  | 
Target for 2024/25 (2025 calendar year) was achieved. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
4.2.3 | Expand Medical Training in Vulnerable Specialties (Psychiatry) This initiative is focused on growing the number of psychiatry training roles in Health NZ services to 50 per year from 2025 onwards. |  | The 2026 annual recruitment cycle uses a nationally coordinated approach to maximize placement of qualified stage 1 psychiatry trainees across New Zealand | Review of new recruitment process is planned for October 2025.
Key Achievements |  |  |  | 
The new nationally coordinated recruitment process was developed in partnership with the Health NZ Regional Directors of Training and the Royal Australian and New Zealand College of Psychiatrists. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
4.3.1 | Grow Mental Health and Addiction Capacity (Increasing post-graduate clinical psychological training capacity) |  | Conversations are ongoing with tertiary providers about increasing the capacity of their post graduate clinical psychology training programmes for 2026. | Universities, are in discussion with TEC, who make independent decisions about the numbers they train each year. Health NZ will continue to encourage and persuade tertiary providers to increase their intakes.
Key Achievements |  |  |  | 
Target for 2024/25 (2025 calendar year) was achieved. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 15
Priority 4
Address Workforce Needs to Hit Targets
Initiative Number | Description | RAG | Current Activity | Next Steps
4.4.1 | Establish Advanced Practice Roles (Allied Health Scientific & Technical) This initiative supports the development of advanced practice roles across allied health, scientific, and technical professions. |  | Advancing work with Advanced Practice Radiation Therapy workforce Initial support underway for MSK Physiotherapy Advanced Practice roles. | Chief Allied Health Science and Technical-led workshops on 15 July and 2 August 2025 to plan resource allocation.
Key Achievements |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
4.3.2 | Grow Mental Health and Addiction Capacity (Supporting additional NESP volumes) |  | Semester two intake of graduate nurses (NESP) for 2025 academic year (2024/25 financial year) is underway. | Final NESP numbers the 2025 academic year (both Allied and Nursing) will be available in December 2025.
Key Achievements |  |  |  | 
The number of people commencing New Entry to Specialist Practice (NESP) training remains strong, with 200 nurses and 51 occupational therapists and social workers commencing in semester one 2025. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l
Initiative Number | Description | RAG | Current Activity | Next Steps
4.3.4 | Grow Mental Health and Addiction Capacity (Update clinical framework and training resources) |  | Obtained feedback from cultural groups. Literature reviews now being undertaken. | Stakeholder meeting to support continuity of progress in the development of the framework. This framework supports best practice delivery and assessment of co-existing approaches across multiple settings.
Key Achievements |  |  |  | 

## Slide 16
Priority 4
Address Workforce Needs to Hit Targets
Initiative Number | Description | RAG | Current Activity | Next Steps
4.4.3 | Establish Advanced Practice Roles (Peer Support Specialists in Emergency Departments, Mental Health) |  | Planning underway for the remaining three to go live: North Shore, Tauranga, and Dunedin. | Dunedin expected to go live late August and others expected to go live in late October 2025.
Key Achievements |  |  |  | 
Five of the eight Emergency Departments are now live: Counties Manukau, Te Toka Tumai Auckland, Wellington, Christchurch and Waikato. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l
Initiative Number | Description | RAG | Current Activity | Next Steps
4.4.2 | Establish Advanced Practice Roles (RN prescribers) This initiative supports the development of Registered Nurse (RN) prescriber roles to enhance primary health care capacity. |  | Draft map created showing RN prescriber distribution across priority areas Nursing Council reviewing RN prescriber education and scope Planning postgraduate scholarships for 120 primary healthcare RNs annually from 2026, including prescribing content as part of the Primary Care Tactical Action Plan initiatives | Refine mapping to distinguish primary healthcare vs Health NZ RN prescribers. Finalise and develop the scholarship pathway framework Scholarship applications open in September 2025
Key Achievements |  |  |  | 
Draft map completed Education grant pathway paper in progress |  |  |  | 

## Slide 17
Priority 4
Address Workforce Needs to Hit Targets
Initiative Number | Description | RAG | Current Activity | Next Steps
4.7 | Keep Our People While Training Overseas Advanced offers for Fellows This initiative supports the retention of health professionals who train overseas by offering advanced opportunities to return and work in Aotearoa. |  | Scoping the implementation plan, including templates, guides, and district-specific needs such as communications planning. | Finalise and approve the implementation plan.
Key Achievements |  |  |  | 
Initial scope approved, paving the way for rollout. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l
Initiative Number | Description | RAG | Current Activity | Next Steps
4.6 | Make Better Use of Overseas-Trained Staff Continue to support 10 NZREX Doctors per year through each of the primary care pathway and NZREX bridging programmes. |  | Draft agreements sent to Capital & Coast, Hutt Valley, and Wairarapa districts for 8 NZREX doctors. Finalising cohort numbers with Auckland Metro, Canterbury, Tairāwhiti, and MidCentral districts. | Confirm and formalise agreements for the October 2025 cohort.
Key Achievements |  |  |  | 
10 overseas-trained doctors appointed to start in Waikato on 7 July 2025. |  |  |  | 

## Slide 18
Priority 5
A Workforce that reflects community need
Initiative Number | Description | RAG | Current Activity | Next Steps
5.1 | Adopt Common Cultural Safety Expectations |  | Gender Affirmation Policy and Diversity Policies developed Rainbow awareness training and e-learning developed Launch of National diversity and inclusions intranet hub | Publication and implementation of policies Launch of Pacific e-learning
Key Achievements |  |  |  | 
15 training sessions delivered to Health NZ teams to support cultural safety expectations |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
5.3 | Invest Appropriately in Māori Focused Programmes This initiative supports programmes that strengthen the Māori health workforce pipeline. |  | Reviewing existing programme and investment and renewing support for those with proven impact. | Continue progressing the renewal process and finalise the investment paper.
Key Achievements |  |  |  | 
Strategic shift toward funding programmes that effectively grow Māori workforce capacity. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l

## Slide 19
Priority 5
A Workforce that reflects community need
Initiative Number | Description | RAG | Current Activity | Next Steps
5.5 | Invest Appropriately in Pacific Focused Programmes. This initiative supports Pacific health workforce development through targeted education and pilot programmes. |  | Cohort 1 and Cohort 2 of the Level 3 ‘Stay Well Stay Strong’ Diabetes Programme training delivered to 21 Kaiāwhina in Pacific providers Diploma in Nursing (Pacific) Cohort 2 underway Foot Care Assistant Pilot Programme in development All contracts for 2024–2025 have been delivered | Complete Cohort 3 and Cohort 4 of the Level 3 ‘Stay Well Stay Strong’ Diabetes Programme by June 2026. Launch Footcare Assistant programme by June 2026. Review funding and evaluate future programme opportunities.
Key Achievements |  |  |  | 
Over 90% pass rate for the Diabetes Stay Well to Stay Strong Level course Nursing graduates for Diploma in Nursing (Pacific) achieved 100% pass rate for NZ State Exam Foot Care Assistant pilots launched in Counties Manukau and Northland districts 777 students engaged through Northern Region health science academies (Year 11, Year 12 and Year 13) |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l
Initiative Number | Description | RAG | Current Activity | Next Steps
5.7 | Establish Rural Training Hubs This initiative aims to set up Rural Training Hubs (RTHs) to strengthen health workforce development in rural communities. |  | Working with community leaders to identify the location of the first rural training hub. | Engage with regional leaders to identify hub locations. First hub location to be confirmed by 30 September 2025 Finalise the model for Rural Training Hubs.
Key Achievements |  |  |  | 

## Slide 20
Priority 5
A Workforce that reflects community need
Initiative Number | Description | RAG | Current Activity | Next Steps
5.8 | Support Workforce into Rural Settings. This initiative focuses on enabling health professionals to transition into rural roles through targeted support. |  | Forming a Clinical Stakeholder Group to guide the scope and support package. | Convene the stakeholder group Explore options to utilise existing programmes to build the resources
Key Achievements |  |  |  | 
Identified resources that can be accessed at no extra cost. |  |  |  | 
Initiative Number | Description | RAG | Current Activity | Next Steps
5.9 | Increase Rural Hospital Medical Specialist Training and Support This initiative aims to strengthen specialist training and support for Rural Hospital Medicine across Aotearoa. |  | Gathering insights to complete a Discovery Report that identifies barriers to training. | Finalise and share the Discovery Report to inform future actions.
Key Achievements |  |  |  | 
Established a collaborative approach with the Division of Rural Hospital Medicine. |  |  |  | 
Completed | In progress | At risk - risk under control | At risk – escalation required | High Risk of non-delivery
l | l | l | l | l