Shorter stays in emergency departments 													Q2 2024/25

2030 target = 95%																	Oct – Dec 2024

Results by region

Te Waipounamu 78.4 per cent

Te Manawa Taki 75.5 per cent

Northern 70.8 per cent

Central | Te Ikaroa 60.1 per cent

Results by district

West Coast 			94.6 per cent

Tairāwhiti			92. 8 per cent

South Canterbury 		88.4 per cent

Lakes 				84.7 per cent

Northland 			82.6 per cent

Whanganui 			79.7 per cent

Canterbury			78.9 per cent

Nelson Marlborough		77.9 per cent

Bay of Plenty 			75.9 per cent

Southern 			74.3 per cent

Taranaki 			73.0 per cent

Hawke’s Bay			70.7 per cent

Counties Manukau		69.1 per cent

Auckland 			68.4 per cent

Waikato 			68.0 per cent

Waitematā 			67.4 per cent

Hutt Valley 			62.7 per cent

Wairarapa 			60.8 per cent

MidCentral			51.9 per cent

Capital and Coast		46.5 per cent

This measure reports patients admitted, discharged or transferred from an ED within six hours as a percentage of all patients who attended ED.

National result 72.1 per cent

Milestone 74 per cent

Target 95 per cent

Results compared with Q1 2024/25

|  | Q1 2024/25 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Shorter stays in ED <6hrs | 67.5 % | 72.1 % | 4.6 % |

Emergency department attendances

Q1 2024/25 = 334,208

Q2 2024/25 = 332,110

Results compared with Q2 2023/24

|  | Q2 2023/24 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Shorter stays in ED <6hrs | 69.7 % | 72.1 % | 2.4 % |

Q2 overview

Emergency department presentations are increasing over time. Presentations are largely increasing in urgent triage categories and decreasing in less urgent triage categories. An increasing proportion of presentations are older, complex patients, who are more likely to stay in the emergency department longer and subsequently be admitted to hospital.

Recent initiatives such the opening of transit lounges in North Shore and Palmerston North hospitals and an ED observation unit in Canterbury are supporting improvements in performance for the shorter stays in emergency departments target. A new High Dependency Unit in Wellington will improve flow in future quarters.

West Coast saw a big improvement in Q2 moving to 94.6% of target, compared to 86.3% in Q1.

Health New Zealand

Te Whatu Ora

*Quarter 1 reported position

Factsheets contain figures used in Quarter 2 report. Health target data changes over time and there may be slight discrepancies between reports dependent on their time of publication

Shorter wait times for elective treatment 													Q2 2024/25

2030 target = 95%																	Oct – Dec 2024

Results by region

Te Manawa Taki 64.2 per cent

Central | Te Ikaroa 62.1 per cent

Te Waipounamu 58.5 per cent

Northern 55.9 per cent

National result 59.2 per cent

Milestone 63 per cent

Target 95 per cent

Results by district

Waikato 				73.4 per cent

MidCentral 				73.1 per cent

Bay of Plenty 				72.8 per cent

Waitematā				68.8 per cent

Capital and Coast			65.4 per cent

South Canterbury			64.0 per cent

Hawke’s Bay 				62.7 per cent

Canterbury 				62.3 per cent

Wairarapa				61.4 per cent

Lakes 					57.7 per cent

West Coast 				56.1 per cent

Southern				54.8 per cent

Nelson Marlborough			54.3 per cent

Hutt Valley 				53.7 per cent

Counties Manukau			53.1 per cent

Northland 				53.1 per cent

Auckland 				53.8 per cent

Whanganui 				49.1 per cent

Taranaki				44.8 per cent

Tairāwhiti				40.9 per cent

This measure presents the proportion of people given a commitment to treatment waiting less than four months as a proportion of all people waiting for a procedure.

Results compared with Q1 2024/25

|  | Q1 2024/25 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Shorter wait times for elective treatment | 62.2 % | 59.2 % | - 3 % |

Elective treatment wait numbers

People waiting end of Q2 2024/25 84,989

Waiting less than 4 months = 50,283

Results compared with Q2 2023/24

|  | Q2 2023/24 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Shorter wait times for elective treatment | 62.1 % | 59.2 % | -2.9 % |

Q2 overview

We’re working to ensure 95 per cent of people have their elective treatment within four months. This means less waiting and faster relief, helping people get back to doing what they love.

Whilst this quarter has seen an overall decline in this target, Waikato appears to be on a steady upwards trajectory, currently sitting at 73.4 per cent.

Over the quarter, there has been increased focus on monitoring performance of routine priority bookings.

A recent boost to outsourcing and insourcing will increase the number of procedures we are able to deliver. Districts and regions have also established theatre productivity and efficiency programmes to optimise capacity. This includes a focus on increasing theatre utilisation, driving down cancellations and theatre late starts / early finishes.

Health New Zealand

Te Whatu Ora

*Quarter 1 reported position

Factsheets contain figures used in Quarter 2 report. Health target data changes over time and there may be slight discrepancies between reports dependent on their time of publication

Faster cancer treatment			 													Q2 2024/25

2030 target = 95%																	Oct – Dec 2024

Results by region

Central | Te Ikaroa 88.7 per cent

Northern 86.8 per cent

Te Waipounamu 85.0 per cent

Te Manawa Taki 82. 6 per cent

National result 85.9 per cent

Milestone 86 per cent

Target 95 per cent

Results by district

Lakes 					98.4 per cent

Wairarapa 				95.8 percent

Whanganui 				92.6 per cent

Hutt Valley				91.6 per cent

Capital and Coast			89.5 per cent

Northland 				89.0 per cent

Waitematā 				88.4 per cent

MidCentral 				88.3 per cent

Auckland 				88.2 per cent

Bay of Plenty 				87.3 per cent

Canterbury				86.8 per cent

South Canterbury 			86.6 per cent

Nelson Marlborough			86.1 per cent

Taranaki 				84.8 per cent

Tairāwhiti 				84.0 per cent

Southern				83.9 per cent

Counties Manukau			82.6 per cent

Hawke’s Bay				80.6 per cent

Waikato 				76.4 per cent

West Coast				74.1 per cent

This measure shows the proportion of eligible cancer patients who received their first treatment within 31 days of a health professional’s decision to treat.

Results compared with Q1 2024/25

|  | Q1 2024/25 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Faster cancer treatment <31 days | 84.6 % | 85.9 % | 1.3 % |

Cancer patients receiving treatment

Treated in Q2 2024/25 = 4,546

Treated within 31 days = 3,903

Results compared with Q2 2023/24

|  | Q2 2023/24 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Faster cancer treatment <31 days | 85.7 % | 85.9 % | 0.2 % |

Q2 overview

Cancer treatment is critical and every day counts. Our target is to ensure 90 per cent of cancer patients start their treatment within 31 days of deciding on a treatment plan. Starting treatment early gives patients the best chance of recovery and improves outcomes. By addressing variation in access to care, improving infrastructure, data and digital tools and strengthening the cancer workforce we’re making sure cancer treatment can start sooner. Positively, Lakes, Wairarapa, Whanganui and Hutt Valley are already exceeding the 90 per cent target.

With Pharmac now funding ten new cancer medicines, people can get faster access to the care they need once a decision is made to treat.

Across the country we’re working to improve performance through initiatives like a new nurse-led chemotherapy infusion unit opened at Bay of Islands Hospital reducing the need for patients to travel to Whangārei.

Health New Zealand

Te Whatu Ora

*Quarter 1 reported position

Factsheets contain figures used in Quarter 2 report. Health target data changes over time and there may be slight discrepancies between reports dependent on their time of publication

Shorter waits for first specialist assessment (FSA)												Q2 2024/25

2030 target = 95%																	Oct – Dec 2024

Results by region

Central | Te Ikaroa 65.2 per cent

Northern 63.3 per cent

Te Waipounamu 59.0 per cent

Te Manawa Taki 55.3 per cent

National result 60.6 per cent

Milestone 62 per cent

Target 95 per cent

Results by district

Lakes 					94.7 per cent

South Canterbury			86.0 per cent

MidCentral				78.1 per cent

West Coast 				73.2 per cent

Capital and Coast 			67.9 per cent

Counties Manukau			67.7 per cent

Auckland 				66.4 per cent

Wairarapa 				65.0 per cent

Tairāwhiti 				62.4 per cent

Hutt Valley 				61.0 per cent

Canterbury 				59.4 per cent

Southern 				58.1 per cent

Hawke’s Bay 				57.6 per cent

Waitematā 				56.8 per cent

Whanganui 				55.7 per cent

Northland 				55.0 per cent

Waikato				54.3 per cent

Nelson Marlborough			51.0 per cent

Bay of Plenty				49.5 per cent

Taranaki				47.2 per cent

This measure presents the proportion of people waiting less than four months for their FSA from the date of referral.

Results compared with Q1 2024/25

|  | Q1 2024/25 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Shorter wait times for FSA | 61.2 % | 60.6 % | -0.6 % |

FSA wait numbers

People waiting end of Q2 2024/25 = 14,891

Waiting less than 4 months = 119,439

Results compared with Q2 2023/24

|  | Q2 2023/24 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Shorter wait times for FSA | 63.5 % | 60.6 % | -2.9 % |

Q2 overview

Reducing the number of missed first specialist assessments is critical to achieving our health target. Whilst this quarter has seen a general decline in this target, Lakes continues to lead the way, sitting very close to the goal at 94.7 per cent.

A state-of-the-art ear, nose and throat mobile van commenced operation in Northland this quarter and a complete cataract care pathway launched at Kaitaia Hospital in September 2024 and is focused on reducing wait times and provides for up to 20 patients per month to receive end-to-end care.

Waitlist review and validation are an ongoing process and include both operational review (ensuring waitlists are accurate, and patients have been ‘exited’ appropriately) and clinical review of waitlists within pressured services and districts.

Health New Zealand

Te Whatu Ora

*Quarter 1 reported position

Factsheets contain figures used in Quarter 2 report. Health target data changes over time and there may be slight discrepancies between reports dependent on their time of publication

Improved childhood immunisations	 													Q2 2024/25

2030 target = 95%																	Oct – Dec 2024

Results by region

Te Waipounamu 85.9 per cent

Central | Te Ikaroa 78.7 per cent

Northern 75.0 per cent

Te Manawa Taki 70.6 per cent

Results by district

Canterbury 				87.8 per cent

Southern 				87.7 per cent

West Coast				84.6 per cent

Capital and Coast			84.5 per cent

Wairarapa 				83.0 per cent

Hutt Valley				79.9 per cent

Nelson Marlborough			77.7 per cent

Auckland 				77.7 per cent

Waitematā 				77.3 per cent

Hawke’s Bay 				76.5 per cent

Taranaki				76.3 per cent

South Canterbury			75.4 per cent

MidCentral 				74.2 per cent

Counties Manukau			73.6 per cent

Whanganui 				71.5 per cent

Waikato 				71.5 per cent

Tairāwhiti 				69.8 per cent

Bay of Plenty 				68.8 per cent

Northland				66.5 per cent

Lakes					66.3 per cent

National result 77.0 per cent

Milestone 84 per cent

Target 95 per cent

This measure shows the percentage of children who have all their scheduled vaccinations by the time they are two years old.

Results compared with Q1 2024/25

|  | Q1 2024/25 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Improved immunisation for children 24mnth | 75.7 % | 77.0 % | 1.3 % |

Number of children fully immunised at 24 months

Eligible babies Q2 2024/25 = 14,891

Fully immunised = 11,462

Q2 overview

Vaccinations are one of the most effective ways to keep you and your child safe. By ensuring that every child is vaccinated, we help protect the health of all New Zealanders.

Immunisation rates have been decreasing steadily over the past few years. This is due to a range of contributing factors, such as vaccine hesitancy, vaccine misinformation/disinformation and barriers to access to vaccinations (including capacity issues within general practice who deliver between 85 – 90 per cent of childhood vaccinations).

While Immunisation has been on a downward trajectory since 2014, the percentage coverage for children at 24 months increased in the last quarter.

Together with our partners across the health sector we are committed to maintaining this momentum and to achieve this we are implementing initiatives across five action areas:

- increasing targeted and opportunistic immunisation for priority populations

- enabling best practice immunisation efforts

- increasing whānau and community engagement

- increasing workforce capacity and capability

- improving data technological capability.

Results compared with Q2 2023/24

|  | Q2 2023/24 | Q2 2024/25 | % change |
| --- | --- | --- | --- |
| Improved immunisation for children 24mnth | 77.2 % | 77.0 % | -0.2% |

Health New Zealand

Te Whatu Ora

*Quarter 1 reported position

Factsheets contain figures used in Quarter 2 report. Health target data changes over time and there may be slight discrepancies between reports dependent on their time of publication